## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Anchal sati | 2024-11-18 | GPU non-availability for YOLO Model Training | S2 | Anchal sati | Logical | Used google collab to trained | 2024-11-15 | Closed | Completed
2 | Anchal sati | 2024-11-13 | Sort module not having class ID | S3 | Anchal Sati | Logical | Used the earlier YOLO Model | 2024-12-10 | Closed | Completed
3 | Anchal sati | 2024-11-26 | Missing detection in some frame | S4 | Anchal sati | User Interface | Interpolated the bounding boxes | 2024-12-21 | Closed | Completed

## Sheet2
Logical
User Interface
Maintainability
Standards
Others